# Introduction

The purpose of the Project Checklist is to define guidance criteria using reference documents and to list the manner in which the project is delivered through different submissions and documents.

# Checklists

Each phase of a project culminates in one or more major milestone submissions (MMS).  The MMS is initially submitted as draft and is later delivered as final after a comment resolution phase.  The MMS is typically comprised of various deliverables and in most cases undergoes a full review by the appropriate Authority departments and engineering groups.

Some deliverables may not be part of the MMS.  These include documents that are updated and reviewed several times throughout the project lifecycle, such as the Project Risk Register, and others that are required for review and approval prior to the MMS, such as the Design Exception Report.  These deliverables are typically reviewed and processed by limited Authority departments and engineering groups.  These documents can be included as part of the MMS as an appendix to the phase report, where applicable, or as individual documents.

# Instructions

The Project Checklists are customizable and allow for the designer and the Authority to add deliverables as necessary.  The checklists are intended to allow for consistent documentation of the anticipated deliverables.

Prior to each MMS, the corresponding Checklist is to be completed by the designer to document the deliverables to be included in each MMS (complete the “Req’d” column) and reviewed with the Authority Project Manager for concurrence.  This checklist shall be submitted with the MMS with each included deliverable affirmed in the checklist (complete the “Incl” column).  The checklist will include the number of hard copies required for each deliverable, as directed by the Authority Project Manager, and reminders for other tasks to be completed to meet related Authority requirements.

The Reference Documents on the following page are numbered and listed in each checklist under the “Ref #” column when such reference document is relevant to that item.

# Reference Documents

Project Checklist without Samples

Project Checklist_June2024_MMS-CD

Project Checklist_MMS-PD_Phase A

Project Checklist_June2024_MMS_FD_Pre-Phase B

Project Checklist_June2024_MMS-FD_Phase B

Project Checklist_MMS-FD_Pre-PhaseC

Project Checklist_MMS-FD_PhaseC

Project Checklist_June2024_MMS-FD_PhaseD

Project Checklist_June2024_MMS-FD_Post-PhaseD

The following are found at https://www.njta.gov/business-hub/professional-services/supplemental-links/ unless otherwise noted:

- Guidance for Electronic and Hard Copy Submittals

- Sample Stakeholder Outreach Plan (provided by NJTA liaison)

- Outside Agency Coordination Log Template

- Design Decision Report Template

- Risk Register Template

- Design Exception Guidance

- Concept Development Report Template

- Preliminary Design Report Template

- Preliminary Design Report Template (Maintenance Repair)

- Shop Drawing Review Guidelines

- CapEx & Specifications Design Guidelines

- Sample Engineer’s Estimate

- Guidance for Creating an Engineer’s Estimate

- As-Built Plan Preparation Guidelines

- Utility Contact Letter Template

- Summary of Permit Requirements

- Utility Status Schedule Template

- Traffic Impact Notices Template

- Road User Cost Manual & Worksheets

- Load Rating Manual

- Highway Agency Stormwater General Permit “Phase D” Checklist (provided by NJTA liaison)

- Materials Acceptance Review Matrix template

- CADD Standards Manual – found at https://www.njta.gov/business-hub/professional-services/engineering-manuals/

- Fiber Optic Cable Design Review Certification Form

- QPL Pilot Form

NJTA Design Manual

- – Structures Design (SECTION 3)

- – Drainage Design (SECTION 5)

- – Geotechnical Engineering (SECTION 6)

- – Signing and Striping (SECTION 7)

- – Lighting and Power Distribution Systems (SECTION 8)

- – Traffic Control During Construction (SECTION 10)

- – Facility Buildings / Toll Plazas (SECTION 12)

- – Environmental Engineering (SECTION 13)

NJTA Procedures Manual

- – Design Surveys (SECTION 4)

- – Geotechnical Engineering (SECTION 5)

- – Roadway Plan Preparation (SECTION 6)

- – Structures Plan Preparation (SECTION 7)

- – Utility Installation, Relocations and Adjustments (SECTION 8)

- – Right of Way (SECTION 9)

- – Traffic Noise Analysis and Abatement (SECTION 10)

- – Constructability Review (SECTION 11)

The following are found at https://www.njta.gov/business-hub/professional-services/supplemental-links/ unless otherwise noted:

- Bridge Inspection Program

- Guidance for Electronic NJDEP DLRP Applications

- Guidelines For Use Of VMS Systems For Construction

- License to Cross Application – found at https://www.njta.gov/forms-records/license-to-cross/

- Multipliers for Professional Services – found at https://www.njta.gov/business-hub/professional-services/

- Sign Request Form

- Supplemental Sign Policy

- Traffic Permit Application

- Supplementary Products List (SPL Form)

- Sample Addendum Files

- Utility Checklist

- Sample Utility Checklist

- Supplemental Utility Order

- Utility Order

- Standard Voltage Drop Computation Form

- Sample Design Plans – found at https://www.njta.gov/business-hub/professional-services/

# Revision Summary

| Revision | Date | Revised by | Summary |
| --- | --- | --- | --- |
| 0 | September 2024 |  | Original document |
| 1 | February 2026 | DCA2026PM-02 | Fixed links to point to www.njta.gov |