## Risk Register
PROJECT RISK REGISTER
[11 empty] | NJTA Project Manager: |  | Roadway(s):
[11 empty] | Design Consultant: |  | Mileposts:
[11 empty] | Designer Project Mgr: |  | Initial Register Date:
[11 empty] | NJTA OPS No.: |  | Last Register Update:
Project Name: |  | SAMPLE | [8 empty] | NJTA Contract No:
Risk Rank & ID |  | Risk Statement & Category |  |  | Risk Analysis Matrix | [5 empty] | Risk Response Strategy & Response Planning
|  |  | Risk Category |  |  | Risk Impact
Risk Rank | Unique ID # | Risk Statement | Initial Risk Owner | Risk May Occur In | Risk Probability | Schedule | Cost | Schedule Score | Cost Score | Final Score | Risk Response Strategy | Risk Response Action Plan | Final Risk Owner | Action Plan Status | Risk Last Updated
As a result of <definite cause>, <uncertain event> may occur, which would lead to <effect on objective(s)>. See samples below.
1 | 1 | As a result of supply chain issues, delays on procurement for project materials may occur, which would lead to delays in project construction. | Construction | Construction | 4 - High | 7 - High | 4 - Moderate | 28 | 16 | 44 | Mitigate Threat | Identify materials with long lead times and work with the Contractor to procure those up front. | Contractor and NJTA | Plan Not Implemented
2 | 2 | As a result of the rising costs of materials & labor, coupled with supply chain issues, increased construction cost for the project may occur. | Construction | Construction | 4 - High | 2 - Low | 7 - High | 8 | 28 | 36 | Accept Threat | Use the latest bid prices to develop realistic cost estimate. Identify recent trends and project costs of certain materials and labor accordingly. | Designer and NJTA | Plan Not Implemented
3 | 3 | As a result of unforeseen substructure conditions/obstructions, execution of deep foundation installation may be hindered, which would lead to increased construction cost and duration. | Geotechnical | Construction | 2 - Low | 4 - Moderate | 4 - Moderate | 8 | 8 | 16 | Accept Threat | Build the appropriate uncertainties into construction cost and schedule during Final Design. | Designer | Plan To Be Developed
Note on I11: Schedule Score = Probability * Schedule Impact
Note on J11: Cost Score = Probability * Cost Impact
Note on K11: Final Score = Schedule Score + Cost Score
Note on L11: Note that each response strategy should be revisited and updated as the project progresses. Threats Avoid Threat - Risk can be avoided by removing the cause of the risk or executing the project in a different way while still aiming to achieve project objectives. Not all risks can be avoided or eliminated, and for others, this approach may be too expensive or time‐consuming. However, this should be the first strategy considered. Transfer Threat - Transferring risk involves finding another party who is willing to take responsibility for its management, and who will bear the liability of the risk should it occur. The aim is to ensure that the risk is owned and managed by the party best able to deal with it effectively. Risk transfer usually involves payment of a premium, and the cost‐effectiveness of this must be considered when deciding whether to adopt a transfer strategy. Mitigate Threat - Risk mitigation reduces the probability and/or impact of an adverse risk event to an acceptable threshold. Taking early action to reduce the probability and/or impact of a risk is often more effective than trying to repair the damage after the risk has occurred. Risk mitigation may require resources or time and thus presents a tradeoff between doing nothing versus the cost of mitigating the risk. Opportunities Exploit Opportunity - The aim is to ensure that the opportunity is realized. This strategy seeks to eliminate the uncertainty associated with a particular upside risk by making the opportunity definitely happen. Exploit is an aggressive response strategy, best reserved for those “golden opportunities” having high probability and impacts. Share Opportunity - Allocate risk ownership of an opportunity to another party who is best able to maximize its probability of occurrence and increase the potential benefits if it does occur. Transferring threats and sharing opportunities are similar in that a third party is used. Those to whom threats are transferred take on the liability and those to whom opportunities are allocated should be allowed to share in the potential benefits. Enhance Opportunity - This response aims to modify the “size” of the positive risk. The opportunity is enhanced by increasing its probability and/or impact, thereby maximizing benefits realized for the project. If the probability can be increased to 100 percent, this is effectively an exploit response. Threats and Opportunities Accept Threat or Opportunity - This strategy is adopted when it is not possible or practical to respond to the risk by the other strategies, or a response is not warranted by the importance of the risk. When the project manager and the project team decide to accept a risk, they are agreeing to address the risk if and when it occurs. A contingency plan, workaround plan and/or contingency reserve may be developed for that eventuality.

## Impact and Probability Metrics
Impact Definitions
Rating --> | Very Low | Low | Moderate | High | Very High
Cost Impact of Threat | Insignificant cost increase | <5% cost increase | 5-10% cost increase | 10-20% cost increase | >20% cost increase
Cost Impact of Opportunity | Insignificant cost reduction | <1% cost decrease | 1-3% cost decrease | 3-5% cost decrease | >5% cost decrease
Schedule Impact of Threat | Insignificant slippage | <1 month slippage | 1-3 months slippage | 3-6 months slippage | >6 months slippage
Schedule Impact of Opportunity | Insignificant improvement | <1 month improvement | 1-2 months improvement | 2-3 months improvement | >3 months improvement
Probability | 1–9% | 10–19% | 20–39% | 40–59% | 60–99%
Risk Matrix
Probability Rating | 5 - Very High | 5 | 10 | 20 | 35 | 50
| 4 - High | 4 | 8 | 16 | 28 | 40
| 3 - Moderate | 3 | 6 | 12 | 21 | 30
| 2 - Low | 2 | 4 | 8 | 14 | 20
| 1 - Very Low | 1 | 2 | 4 | 7 | 10
|  | 1 | 2 | 4 | 7 | 10
|  | Very Low | Low | Moderate | High | Very High
Impact Rating

## Data Validation Sheet
The dropdowns are utilizing "named ranges" each list here is named accordingly, e.g. Initial Risk Owner is iriskowner |  |  | Probability and impacts pulls numbers from the impact and probability matrix, then concatenates the number and word to use in the matrix
| Initial Risk Owner - iriskowner | Risk May Occur In - rmayoccurin | Risk Probability |  | rprob | Risk Impact |  | rimp
| Access | Concept Development | Very Low | 1 | 1 - Very Low | Very Low | 1 | 1 - Very Low
| Bicycle Pedestrian | Preliminary Design | Low | 2 | 2 - Low | Low | 2 | 2 - Low
| Community Relations | Final Design | Moderate | 3 | 3 - Moderate | Moderate | 4 | 4 - Moderate
| Construction | Construction | High | 4 | 4 - High | High | 7 | 7 - High
| Drainage |  | Very High | 5 | 5 - Very High | Very High | 10 | 10 - Very High
Environmental
Geometric Design
Geotechnical
ITS
Jurisdiction
Maintenance
Procurement
Project Management
Right of Way
Structural
Survey
Traffic Engineering
Traffic Operations
Utilities
Other
| Risk Strategy - rstrategy |  | Action Plan - actionplan |  | Final Risk Owner - riskowner
| Avoid Threat |  | No Action Plan |  | Contractor
| Mitigate Threat |  | Plan Not Implemented |  | Contractor and Designer
| Transfer Threat |  | Plan To Be Developed |  | Contractor and NJTA
| Accept Threat |  | Active Plan Implementation |  | Designer
| Exploit Opportunity |  | Plan Implemented |  | Designer and NJTA
| Share Opportunity |  |  |  | NJTA
| Enhance Opportunity |  |  |  | Other
Accept Opportunity

## RevTable
Revision Summary
Revision | Date | Revised by | Summary
0 | June 2024 |  | Original document